## Slide 1: PMKSY-WDC Regional Review Meeting on 15.12.2017 Kozhikode

## Slide 2: Financial Progress

## Slide 3
IWMP Fund Release & Expenditure |  |  |  |  | 
Batch | Block | Fund Released to PIA Since Inception (In lakh) | Expenditure | Balance (in Lakhs) | reported Balance
2 | AREAKODE | 214.730 | 264.220 | -49.490 | 0.93
2 | AREAKODE | 261.120 | 227.935 | 33.185 | 0.61
3 | AREAKODE | 122.090 | 117.492 | 4.598 | 0.50
3 | KUTTIPPURAM | 211.530 | 211.533 | -0.003 | 0.34
4 | WANDOOR | 89.760 | 98.651 | -8.891 | 0.18
4 | VENGARA | 104.930 | 106.853 | -1.923 | 0.23
5 | WANDOOR | 72.230 | 66.048 | 6.182 | 0.15
6 | KONDOTTY | 36.920 | 36.854 | 0.066 | 0.13
2 | THUNERI | 253.000 | 257.757 | -4.757 | Not showing Balance
4 | BALUSSERI | 104.981 | 105.020 | -0.039 | 
4 | KUNNAMANGALAM | 134.976 | 136.820 | -1.844 | 
6 | KODUVALLY | 51.000 | 53.174 | -2.174 | 
2 | KALPETTA | 157.954 | 168.006 | 0.023 | 0.02
2 | KALPETTA | 179.599 | 198.712 | 0.021 | 0.02
2 | KALPETTA | 190.261 | 199.682 | 0.043 | 0.04
2 | SULTHAN BATHERY | 14.635 | 14.980 | 0.055 | 0.05
4 | KALPETTA | 199.950 | 209.390 | 0.082 | 0.08

## Slide 4
IWMP Fund Release & Expenditure |  |  |  |  | 
Batch | Block | Fund Released to PIA Since Inception (In lakh) | Expenditure | Balance (in Lakhs) | reported Balance
2 | Payyannur | 337.070 | 336.450 | 0.620 | 0.62
3 | Iritty | 58.420 | 58.390 | 0.030 | 0.03
3 | Irikkur | 84.730 | 84.460 | 0.270 | 0.27
4 | Iritty | 49.900 | 49.780 | 0.120 | 0.12
5 | Irikkur | 53.130 | 53.060 | 0.070 | 0.07
6 | Thaliparamba | 29.020 | 29.000 | 0.020 | 0.02
2 | Prappa | 149.820 | 137.500 | 12.320 | 12.32
2 | Prappa | 207.700 | 228.253 | -20.553 | -20.55
2 | Prappa | 284.159 | 289.324 | -5.165 | -5.17
2 | Prappa | 167.063 | 154.160 | 12.903 | 12.90
3 | Karaduka | 105.760 | 99.639 | 6.121 | 6.12
5 | Kasargod | 38.920 | 31.522 | 7.398 | 7.40
6 | Kasargod | 9.000 | 17.315 | -8.315 | -8.32

## Slide 5: Physical Progress

## Slide 6
Variation in physical reporting and MIS |  |  |  |  |  |  |  |  |  |  | 
Sl No | Item of work | Districts |  |  |  |  |  |  |  |  | 
 |  | Kasargod |  | Kannur |  | Wayanad |  | Kozhikkode |  | Malappuram | 
 |  | Physical reporting | MIS | Physical reporting | MIS | Physical reporting | MIS | Physical reporting | MIS | Physical reporting | MIS
1 | Renovation of old WHS | 0 | 12 | 0 | 4 | 0 | 0 | 3 | 136 | 8 | 6
2 | Construction of new farm ponds, tanks etc | 0 | 4 | 0 | 0 | 5 | 5 | 0 | 0 | 19 | 1
3 | Construction of new ground water recharge structures (well recharge) | 0 | 4 | 57 | 38 | 3 | 0 | 121 | 200 | 635 | 52
4 | Construction ofWHS (roof top) /Others | 0 | 19 | 16.15 | 0 | 141.7 | 56 | 64.12 | 0 | 125.9 | 554
5 | Construction of check dam | 0 | 2 | 2 | 2 | 1 | 1 | 4.25 | 0 | 5 | 3
6 | Plantation/afforestation | 0 | 0 | 0 | 0 | 0 | 56 | 40.66 | 4003 | 9.27 | 8.42
7 | Area brought under irrigation | 0 | 0 | 16 | 0 | 436.11 | 0 | 0 | 0 | 193.71 | 0

## Slide 7
First Installment of Central and State Share
Budget allocation for PMKSY –WDC for 2017-18 is Rs. 19.22 Cr. (Central Share)
1st Installment of fund release from DoLR is Rs. 11.53 Cr.
Total release under 1st Installment, including State Share, is Rs. 19.21 Cr. (Not yet received in SLNA account)
Pending for transfer credit
Proposed fund utilization pattern
1st priority is to pending liabilities to the tune of Rs. 11.40 Cr.
Second Priority – Completion of Batch II Projects
Third Priority – Completion of ongoing works of Batch III to VI
Submission of UC
UC for funds released as 1st installment should be furnished within 15days on receipt of the funds from SLNA., after ensuring 100% Utilization.

## Slide 8: NRM Convergence with MgNREGS

## Slide 9: Malappuram
Sl. No. | Project | No. of Works identified | No. of Works in LB | Started | Completed | Remarks
1 | Areakode | 1 | 1 | 1 | 1 | 
2 | Areakode | 3 | 3 | 3 | 0 | 
3 | Areakode | 16 | 12 | 2 | 0 | 
4 | Kuttippuram | 29 | 29 | 0 | 0 | 
5 | Wandoor | 60 | 60 | 0 | 0 | 
6 | Vengara | 186 | 186 | 4 | 3 | 
7 | Wandoor | 51 | 51 | 2 | 2 | 
8 | Kondotty | 9 | 9 | 3 | 0 | 

## Slide 10: Kozhikkode
Sl. No. | Project | No. of Works identified | No. of Works in LB | Started | Completed | Remarks
1 | Thuneri | 16 | 2 | 0 | 0 | 
2 | Balusseri | 29 | 20 | 0 | 0 | 
3 | Kunnamangalam | 18 | 18 | 1 | 0 | 
4 | Koduvally | 1 | 1 | 1 | 1 | 

## Slide 11: Wayanad
Sl. No. | Project | No. of Works identified | No. of Works in LB | Started | Completed | Remarks
1 | Kalpetta | 55 | 55 | 0 | 0 | 
2 | Kalpetta | 35 | 35 | 1 | 0 | 
3 | Kalpetta | 89 | 89 | 1 | 0 | 
4 | Sulthan Bathery | 40 | 40 | 1 | 0 | 
5 | Kalpetta |  |  |  |  | DPR not prepared

## Slide 12: KANNUR
Sl. No. | Project | No. of Works identified | No. of Works in LB | Started | Completed | Remarks
1 | Payyannur | 8 | 2 |  |  | 
2 | Iritty | 10 | 0 |  |  | 
3 | Irikkur | 7 | 0 |  |  | 
4 | Iritty | 8 | 0 |  |  | 
5 | Irikkur | 7 | 1 |  |  | 
6 | Taliparamba | 0 | 0 |  |  | List not prepared

## Slide 13: KASARGOD
Sl. No. | Project | No. of Works identified | No. of Works in LB | Started | Completed | Remarks
1 | Parappa | 37 | 37 | 18 | 10 | 
2 | Parappa |  |  |  |  | 
3 | Parappa |  |  |  |  | 
4 | Parappa |  |  |  |  | 
5 | Karadukka | 36 | 36 | 36 | 36 | 
6 | Kasargod | 22 | 22 | 22 | 10 | 
7 | Kasargod |  |  |  |  | DPR not finalised

## Slide 14
Works requiring labour component be executed first.
Works requiring material component be started after taking into consideration of material – labour ratio.
Works may be completed by February.
Details of works completed be uploaded in the MIS by the DEO of WCDC/TE/Accountant
PDs should monitor and provide logistics for taking up IWMP works under MGNREGA
Strategy for Convergence with MGNREGA

## Slide 15: Details of Batch II projects to be phased out this year
District | Name of project | Fund requirement (reported earlier) | Fund requirement reported recently | Remarks
Malappuram | Areekode | 66.68 | 41.35 | 
 | Areekode | 92.15 | 17.9 | 
Kozhikode | Thuneri | 45 | 10.5 | 
Wayanad | Kalpetta | 55.08 | 55.08 | 
 | Kalpetta | 38.4 | 38.4 | 
 | Kalpetta | 59.31 | 59.308 | 
 | Sulthan Bathery | 50.02 |  | Not furnished
Kannur | Payyannur | 55.21 |  | 
Kasargod | Parappa | 27.5 |  | 
 | Parappa | 26.5 |  | 
 | Parappa | 24 |  | 
 | Parappa | 31 |  | 

## Slide 16: Strategy for Completion of Batch II projects
Assess the remaining activities to be undertaken as per the qualitative and timely completion of projects with available resources.
If any works are to be started for qualitative and timely completion of phase II projects, such works shall be commenced immediately. Payments for such works shall be met from II installment of Central & State Assistants.
No new works shall be taken up under Livelihood and EPA

## Slide 17: Strategy for Completion of Batch II projects ..Contd
Funds will be released on receipt of the actual requirement of above works.
Undertake only those activities that can be completed by Feb 2018.
Complete all activities including those under convergence before Feb 15th 2018.
Submit the completion report by Feb 28th 2018.

## Slide 18: PFMS roll out
One day training for PFMS may be arranged at district level by PDs.
WDT Staff, Clerk in charge of IWMP, EO (WW), shall participate.
Sessions will be handled by functionaries trained at SIRD.
Presentation for making expenditure, advances, fund transfer etc will be provided by SLNA.
PFMS Training be conducted in December itself.
Details on Expenditure as per MPR, admin cost etc from 2016-17 onwards pending PFMS updation we brought for training for making online PFMS entry as part of training.
Computer @ one per block may be arranged for training.
Expenditure shall be met from capacity building component of the Programme fund.
Detailed instructions will be issued by SLNA.

## Slide 19: PRICE (Project Information and Cost Estimation)
PRICE software has been developed by NIC for preparation of estimates under IWMP
It shall be rolled out before 20.12.2017
User ID has been created for all the IWMP Project Engineers for preparation of Estimate.
All the future estimate shall be prepared in PRICE.
PDs shall arrange a half day orientation session for IWMP project engineers. AXE/AE may be directed to handle sessions.

## Slide 20
MIS updation

## Slide 21: MIS-PIA not yet reported upto 2017-18 Nov Physical Progress
Following blocks are lagging in MIS updation.
Blocks indicated in red color have not made any entries
No. | Programme District | No. of Projects | Project Name
1 | Malappuram | 8 | Areekode-1,2,3, Kuttippuram, Wandoor-1,2, Vengara , Kondotty
2 | Kozhikode | 4 | Tuneri, Balusseri, Kunnumangalam, Koduvally
3 | Wayanad | 5 | Kapetta-1,2,3, Sulthanbatheri, Kalpetta-4
4 | Kannur | 6 | Payyannur, Iritty-1&2, Irikkur-1&2, Taliparamba
5 | Kasargode | 7 | Parappa-1,2,3,4, Karadukka, Kasargode-1& 2

## Slide 22: MIS-PIA not yet reported upto 2017-18 Nov Financial Progress
Blocks indicated in red color have not made any entries
No. | Programme District | No. of Projects | Project Name
1 | Malappuram | 8 | Areekode-1,2,3, Kuttippuram, Wandoor-1,2, Vengara , Kondotty
2 | Kozhikode | 4 | Tuneri, Balusseri, Kunnumangalam, Koduvally
3 | Wayanad | 5 | Kapetta-1,2,3, Sulthanbatheri, Kalpetta-4
4 | Kannur | 6 | Payyannur, Iritty-1&2, Irikkur-1&2, Taliparamba
5 | Kasargode | 7 | Parappa-1,2,3,4, Karadukka, Kasargode-1& 2